## Sheet1 (hidden)
Modules | Roles | Links | Username | Password
Revenu | Payment portal | https://ananportal.azurewebsites.net/ | 1 | '07068006051
| ANAN staff Login (Ag. Reg. Finance and Account) | https://ananfe.azurewebsites.net/ | fikfikky@gmail.com | Fikayo
Payment Voucher
| Ag. Reg. Finance & Acct | https://ananfe.azurewebsites.net/ | fikfikky@gmail.com | Fikayo
| Review Officer |  | paul@gmail.com | Fikayo
| Cashier |  | solomon@gmail.com | Fikayo
| Registrar |  | itunu@gmail.com | Fikayo
| Final Account |  | sheghun@gmail.com | Fikayo
| PV Officer |  | sheghunoladiran9@gmail.com | Fikayo
| Internal Audit |  | segun@gmail.com | Fikayo

## login
POCR
Roles | Links | Username | Password
USER LOGIN | https://pocr.bpp.gov.ng | graceejegwa@yahoo.com | password
BPP ADMIN LOGIN | https://pocr.bpp.gov.ng | poms@bpp.gov.ng | POMS@dm33n
POMS
BPP ADMIN LOGIN | https://poms.bpp.gov.ng/admin | info@bpp.gov.ng | P@ssword1
USER LOGIN | https://poms.bpp.gov.ng | grayceecharles@gmail.com | password

## POMS
Sub-modules | Pending Issues | Status | Resources | Timeline | Date
Kick-off session | Process Analysis, Planning and task assignment | DONE | Project Team | 2hrs | 9th July
BIODATA SECTION | Change Middle Name to Other Names | DONE | FE/BE | 1 Hr | 9th July
| Change Date of Employment to date of First Appointment | DONE | FE/BE | 2 hrs | 9th July
| Add quantity to products(Annual Subscription). | DONE | FE/BE | 1.5 days | 11th July
| Add FCSC File Number | DONE | FE/BE
| Add BPP File Number | DONE | FE/BE
| Add IPPIS Number | DONE | FE/BE
| Add NHIS Number | DONE | FE/BE
| Add NHF Number | DONE | FE/BE
| Have you been converted? If yes, provide date and year of Gazette | DONE | FE/BE | 3 hrs | 12th July
| edit of biodata should be disabled on registration and should be subjected to approval | PENDING
| Have you been certified to come before Have you been converted | DONE | FE | 2 hrs | 12th July
EXIST ALREADY | Add email address | PENDING | FE/BE | 1.5 Days | 14th July
| Add Gender (male or Female) | DONE | FE/BE
| Add married, Single, Widower or Divorced | DONE | FE/BE
| Local Government Area should under Biodata | DONE | FE/BE
| Add Residential Home Address | DONE | FE/BE
| Add Permanent Home Address | DONE | FE/BE
| Add ‘Step’ beside Salary Grade Level | DONE | FE/BE | 1.5 days | 16th July
| Add Date of increment (Default is January 1 every year) | DONE | FE/BE
| Two Next of Kin’s with their Names, Address, Phone Number and Relationship | DONE | FE/BE
| Date of Birth column should only accept values for 18years and above | DONE
| Add Date of Confirmation of appointment | DONE | FE/BE | 1 Day | 17th July
| Add Federal Loans Board Number | DONE | FE/BE
| Add Establishment Number | DONE | FE/BE
| Add Date of Gazette of First appointment | DONE | FE/BE
CAREER MOBILITY SECTION | Remove Local Government from Section | DONE | Frontend only but backend needs to check if it's a required field | 1 Hr | 9th July
| Add Country with a drop down to select from list | DONE | FE/BE | 1 Day | 10th July
| For other countries apart from Nigeria, indicate State/county or address | DONE | FE/BE
| Add Ref.No. and Circular Date for posting | DONE | FE/BE
| After each posting by BPP, Admin should be able to trigger action (email, SMS alert) notifying officers on posting, giving them one week to update their records | PENDING | FE/BE | 2 Days | 12th July
| Posting Assumption Date From … To…. | DONE | FE/BE | 1 Day | 13th July
| Add Division, Section, Unit | DONE | FE/BE
| Expected Retirement Date | DONE | FE/BE
| Add Cadre on first appointment | DONE | FE/BE
| Add Date of last promotion | DONE | FE/BE
Posting Status |  | DONE | FE/BE | 1 Day | 14th July
| Indicate whether 1st term or 2nd term if Secondment | DONE | FE/BE
| If Secondment is selected, remove repetition of data input (MDA, File Number, state, etc.) | DONE | FE | 1 Day | 15th July
| If Secondment is selected, remove upload of Appointment and Confirmation Letters. Leave only Promotion Letter | DONE | FE
| Add Name of Director or Head of Department | DONE | FE/BE | 1 Day | 16th July
| System to flag overstay by officer in an MDA (Maximum is 2 years) | PENDING | FE
| Admin to generate Report on Overstayed officers based on system flagging | PENDING | FE/BE | 3 Days | 21st July
| Under Career mobility section, user should be able to add projects, not just a text box as it is now | DONE | FE/BE | 2 Days | 23rd July
| Maintain BPP*, IPPIS*, Establishment, FCSC remove others | PENDING
| Make country field optional | PENDING
| change reference number to circular reference number | PENDING
| make division, section and unit fields optional | PENDING
| Make Director/HOD field optional | PENDING
| make start and end date optional and they are only required if secondment is selected | PENDING
| show start and end date if secondment is selected | PENDING
| Posting Assumption Date From … To…. Shold have i still work here option | PENDING
| if posting is selected add date, second and third term | PENDING
ACADEMIC QUALIFICATIONS | Add ’Name of’ to ‘Institution’ | DONE | FE | 30 min | 18th July
| Add Year attended and Year Obtained for qualification (instead of Start and End Dates) | DONE | FE/BE | 2 hrs
PROFESSIONAL QUALIFICATIONS | Add ’Name of’ to ‘Institution | DONE | FE | 30 min
PROCUREMENT OFFICER | Can update information provided on the system from time to time. (create a dashboard page and other pages) | PENDING | FE/BE | 2 Days | 4th August
| Validate registration against xxxxxxxxxx and send confirmation link to email | DONE | FE/BE | 3 Days | 7th August | they can add email password and BPP File Number
| Notify admin of information updated in the system by the officer | PENDING | FE/BE | 2 Days | 13th August
BPP ADMIN | Notified of new registration | PENDING | FE/BE | 2 Days | 15th August
| Change status of officer from unverified to verified officer | DONE | FE/BE | 2 Days | 11th August
| Report Generation for Procurement Officers by:  Grade level -DONE  Age/Sex  Verified/Unverified - DONE  Academic/Professional Qualification  Date of First Employment  Date of MDA Deployment  Year of Conversion  State of Origin | PENDING | FE/BE | 4 Days | 20th August
| Report Generation for Procurement Officers within and outside the poll | PENDING | FE/BE | 4 Days | 20th August
| Mr. Debo and Mr. Yinka should be able to generate BPP number for the Poll(old procurement officer) | PENDING
| change due for posting to expected retirement date | PENDING
| Check career progression | PENDING
| User should get approval from admin BPP on biodata update | PENDING
| Bpp should be able to turn off/on the edit biodata | PENDING
BPP SERVER | Migration of applications to BPP server. | PENDING | Devops
JUSTIFICATION | This is in order for application to capture more information about the procurement officers registered on the application.
Impact of Not Implementing Proposed Change | Some basic information will be omitted from the officer’s profile

## POCR
Features | Test Case | Result | Priority
1. Proposed Change Description and References: | 1. . Downloads should include Introductory Notes, Lecture Notes, Assignment No. 1, Assignment No. 2, Other Documents and Further downloads which includes (Executive Order E01, Executive Order-E05, Public Procurement Regulations for Goods and Works, SGF Circular of 3rd June 2009, SGF Circular of 6th January 2012, SGF Circular of 6th September 2013 (003), SGF Circular Procurement Processing Time) – (16hrs) | DONE
| Submission to be made to the email ‘procurementcadre@bpp.gov.ng’ and NOT ínfo@bpp.gov.ng’ – (10mins) | DONE
| Download button should be ‘Downloads’ a click of which takes user to a page where all documents enumerated on Number 1 above can be downloaded – (10mins) | DONE
| . Ref. No. for each candidate should follow the pattern – BPP/PCC/MAR/2019/001 where 001 represents a Serial Number to be automatically generated - already done | DONE
Adding instruction for users to ‘Upload’ answers to the two assignments in Number 1 above after downloading (20mins
DONE
Ability to upload documents by participants
Ability to authenticate participant prior to registration
Admin functions to include upload and download of documents, filtering of records/submissions by year, agency, etc.
Justification | This is in order for application to capture more information about the procurement officers registered on the application.
Impact of Not Implementing Proposed Change | Some basis information will be omitted from the officers profile
Justification | The Hard Drives supplied by vendors are not genuine, thus there is need to uninstall them, format the data on them and return to supplier in order for the Bureau to have the value for money on the investment
Impact of Not Implementing Proposed Change | The Bureau will continue to use the refurbished HDD which is prone to shut-down at any momemt, if this happens the Bureau will experience down-tme for a long period of time before a replacement is provided and all the data on them will be lost

## Hardware Provisioning
Feature | Pending Issues | Test result/Status | Priority
Proposed Change Description and References: | 1. Remove the HDD and format
2. Reinstall the operating system
3. Install and Configure two Exsi 6.7 Hos
4. Install window server 2016
5. Install and Configure Vsphere Vcentre 6.7
6. Register all VMs to the new host (so they can point to the SAN)
7. Licensing of the servers
8. Monitor deployment to ensure installations are completed
Decomission old servers